## Slide 1: “Gloves Off” Project Tips and Guidance

## Slide 2: Contents
Top tips on how to challenge glove use.
Project Baseline Measurement Data.
Guidance on sharing information about the “Gloves Off “project with staff, patients and relatives.
Recommended educational resources that can be used to support the project.
Monitoring and evaluating progress with the project.
How to sustain staff engagement with the “Gloves Off” project.
A list of papers, Journals and video links for further information.

## Slide 3: Top Tips To Challenge Inappropriate Glove Use
Think about one small change you can make, whether individually, in your team or in your Ward/Department/Residential Nursing Home/GP practice/Service.
Give staff the power to make their own decisions.
Engage everyone at the beginning, asking for their feedback before anything begins.
Feedback results to staff, so everyone can see their progress.
Remember that it will take time to change the current culture of glove use.
This journey is a marathon and not a sprint.
It is a Team effort!.

## Slide 4: Project Baseline Measurement Data
Collect the following baseline data before the launch of the campaign which can be used to monitor and evaluate the progress with the project’s goals.
Hand hygiene Audit results.
Provided staff questionnaires.
Procurement data regarding the ammount of gloves, hand soap, paper towels and alcohol hand gel used in your work environment over the past financial year and associated costs.

## Slide 5: Guidance On Sharing Information About The Project With Staff, Patients And Relatives
Clear messaging is required.
Highlight the importance of the project objectives- To increase awareness of our glove usage and reduce the number of gloves we wear to achieve better patient outcomes, improve hand hygiene compliance, and reduce our carbon footprint and financial costs associated with glove misuse.
Consider how you will share information about the project with your colleagues e.g. staff briefings/handovers, Staff Meetings, Group WhatsApp chats, e-mails, Notice Boards, screensavers, etc.
Ensure that provided campaign posters are on display in your work area.
Patient and relative information will also need to be considered e.g. patient information leaflet explaining why we are launching the campaign and what to expect.

## Slide 6: Educational Resources To Support The Project
Consider arranging a hand hygiene and Personal Protective Equipment(PPE) training update or event for your Ward/Department/GP Practice/Residential Nursing Home/Service.(e.g. virtual event via MS Teams or an event in your work area).
Invite guest speakers e.g. a member of the Infection Prevention and Control Team, Company Representatives who supply hand soap, alcohol hand gel.
Use the provided educational resources- Frequently asked Question and Answer(FAQ) document, Reading materials and video links included in this project guidance.

## Slide 7: Monitoring and Evaluating Project Progress
Regularly assess the project progress towards its goals.
Different work environments will have different challenges.
It is therefore essential to obtain regular feedback from staff to identify if any aspects of the project requires improvement.

## Slide 8: Project Evaluation at six months:- Measuring the project outcomes against the project goals.
Repeat hand hygiene audits to assess if there is an improvement in hand hygiene compliance.
Obtain procurement data on the number of gloves, hand soap, paper towels and alcohol hand gel used, and the associated costs, six months after the project launch date to determine if we have reduced the number of gloves used and subsequently reduced financial costs and improved our carbon footprint.
Repeat the staff questionnaires six months after the project launch date to assess if staff awareness about glove use has increased and to identify any gaps in learning.
Include any received patient and relative's feedback.
Compare the baseline measurement data collected before the launch of the project with the measurement data collected at 6 months.
Are we achieving the project goals?
Does the project need to be relaunched?

## Slide 9: Sustaining Staff Engagement With The “Gloves Off” Project.
Provide regular feedback to staff about progress with the project.
Organise friendly competitions and challenges related to the project goals.
Acknowledge staff for their achievements (at staff meetings or handovers, awarding a certificate, giving a prize).
Share and celebrate the positive outcomes from the project with your colleagues.

## Slide 10: “Gloves Off” Further information
Journals
Papers
Video links

## Slide 11
Royal College of Nursing (RCN) Glove Awareness
Glove awareness | Campaigns | Royal College of Nursing (rcn.org.uk)
Great Ormond Street Hospital (GOSH)
The gloves are off! | Great Ormond Street Hospital (gosh.nhs.uk)
British Medical Association (BMA)
When the gloves come off (bma.org.uk)
Nursing Times
The impact of glove misuse on patient safety during the Covid-19 pandemic | Nursing Times
NHS England
NHS England » ‘The gloves are off’ campaign

## Slide 12
Nursing Times
Protect the environment by reducing unnecessary glove use, nurses urged | Nursing Times
Environmental impact of personal protective equipment distributed for use by health and social care services in England in the first six months of the COVID-19 pandemic
Environmental impact of personal protective equipment distributed for use by health and social care services in England in the first six months of the COVID-19 pandemic - Chantelle Rizan, Malcolm Reed, Mahmood F Bhutta, 2021 (sagepub.com)
Royal College of Nursing(RCN) Tools of the Trade- Guidance for healthcare staff on glove use and the prevention of work-related dermatitis.
https://www.rcn.org.uk/Professional-Development/publications/tools-of-the-trade-uk-pub-010-218

## Slide 13
Video Links
Hand washing technique - YouTube - Hand washing technique by BMJ Learning.
https://www.youtube.com/watch?v=S9VjeIWLnEg- How to wash your hands NHS song
https://youtu.be/d3EPLfzNM_Q?si=97hOFfTMGusBWkJX - NHS England – How to wash your hands for patients and carers.
Using gloves appropriately in healthcare animation video | IPS
Infection Prevention Society – Using gloves appropriately in healthcare.
https://www.youtube.com/watch?v=OC8MFGu8s94- For a greener NHS Great Ormond Steet Hospital reducing single use plastics case study.
Please also refer to your local Hand Hygiene Policy.